## Agile Kanban Board
BACKLOG | IN PROGRESS | TESTING / QA | DONE
[VCFS-003] Algorithms Assignee: Zaid Task: Develop Availability Parser: Convert continuous blocks to discrete duration slots Due: 2026-03-25 |  |  | [VCFS-002] Core Backend Assignee: Zaid Task: Build State Machine: Dormant -> Preparing -> BookingsOpen -> FairLive Due: 2026-03-21
[VCFS-004] Algorithms Assignee: Zaid Task: Build Tag-Weighted MatchEngine for Auto-Booking collision detection Due: 2026-03-31 | [VCFS-006] Lifecycle Assignee: YAMI Task: Implement Data Purging Routine (Safe clear of ArrayList/HashMap legacy data) Due: 2026-03-22 |  | [VCFS-005] Admin UI Assignee: YAMI Task: Construct AdministratorScreen using Java Swing GridBagLayout Due: 2026-03-19
[VCFS-007] Lifecycle Assignee: YAMI Task: Develop SystemTime Boundary Injector (openTime, closeTime, startTime, endTime) Due: 2026-03-26 | [VCFS-009] Recruiter UI Assignee: Taha Task: Build Dynamic Offer & AvailabilityBlock Creation Form Due: 2026-03-23 |  | [VCFS-013] Candidate UI Assignee: MJAMishkat Task: Develop Registration Screen & simulate session via Email String injection Due: 2026-03-18
[VCFS-008] Logging Assignee: YAMI Task: Implement Central Audit Log Observer & sync to JTextArea stream Due: 2026-03-30 | [VCFS-014] Booking Flow Assignee: MJAMishkat Task: Implement Manual Booking flow via Model queries Due: 2026-03-24 |  | [VCFS-017] Architecture Assignee: Mohamed Task: Visual Paradigm: Execute Round-Trip map of MVC Controller Dependencies Due: 2026-03-19
[VCFS-010] Recruiter UI Assignee: Taha Task: Implement JList with DefaultListModel for dynamic Schedule View Due: 2026-03-27 | [VCFS-018] QA Testing Assignee: Mohamed Task: JUnit 5: Boundary value equivalence testing for VirtualRoom entry/exit Due: 2026-03-25
[VCFS-011] Virtual Room Assignee: Taha Task: Implement CardLayout swap for Schedule View -> Virtual Room View Due: 2026-04-01
[VCFS-012] Virtual Room Assignee: Taha Task: Develop post-session AttendanceOutcome logic (ATTENDED, NO_SHOW, ENDED_EARLY) Due: 2026-04-05
[VCFS-015] Booking Flow Assignee: MJAMishkat Task: Build Auto-Booking Proposal/Acceptance UI View Due: 2026-03-29
[VCFS-016] Virtual Room Assignee: MJAMishkat Task: Develop Lobby Gatekeeper: Cross-reference SystemTimer with Reservation StartTime Due: 2026-04-04
[VCFS-019] QA Testing Assignee: Mohamed Task: JUnit 5: State verification tests for MeetingSession lifecycle Due: 2026-03-31
[VCFS-020] Media Assignee: Mohamed Task: Draft precise 30-min chronological Panopto screencast script covering 12 Use Cases Due: 2026-04-06

## Technical Gantt
Ticket | Epic | Technical Implementation Task | Assignee | Status | % Done | Start | End | 2026-03-16 | 2026-03-17 | 2026-03-18 | 2026-03-19 | 2026-03-20 | 2026-03-21 | 2026-03-22 | 2026-03-23 | 2026-03-24 | 2026-03-25 | 2026-03-26 | 2026-03-27 | 2026-03-28 | 2026-03-29 | 2026-03-30 | 2026-03-31 | 2026-04-01 | 2026-04-02 | 2026-04-03 | 2026-04-04 | 2026-04-05 | 2026-04-06 | 2026-04-07 | 2026-04-08
VCFS-001 | Core Backend | Implement Singleton SystemTimer with Observer Pattern for UI sync | Zaid | Completed | 100% | 2026-03-16 | 2026-03-18
VCFS-002 | Core Backend | Build State Machine: Dormant -> Preparing -> BookingsOpen -> FairLive | Zaid | Completed | 100% | 2026-03-18 | 2026-03-21
VCFS-003 | Algorithms | Develop Availability Parser: Convert continuous blocks to discrete duration slots | Zaid | To Do | 0% | 2026-03-21 | 2026-03-25
VCFS-004 | Algorithms | Build Tag-Weighted MatchEngine for Auto-Booking collision detection | Zaid | In Progress | 60% | 2026-03-25 | 2026-03-31
VCFS-005 | Admin UI | Construct AdministratorScreen using Java Swing GridBagLayout | YAMI | Completed | 100% | 2026-03-16 | 2026-03-19
VCFS-006 | Lifecycle | Implement Data Purging Routine (Safe clear of ArrayList/HashMap legacy data) | YAMI | In Progress | 50% | 2026-03-19 | 2026-03-22
VCFS-007 | Lifecycle | Develop SystemTime Boundary Injector (openTime, closeTime, startTime, endTime) | YAMI | To Do | 0% | 2026-03-22 | 2026-03-26
VCFS-008 | Logging | Implement Central Audit Log Observer & sync to JTextArea stream | YAMI | To Do | 0% | 2026-03-26 | 2026-03-30
VCFS-009 | Recruiter UI | Build Dynamic Offer & AvailabilityBlock Creation Form | Taha | In Progress | 25% | 2026-03-18 | 2026-03-23
VCFS-010 | Recruiter UI | Implement JList with DefaultListModel for dynamic Schedule View | Taha | To Do | 0% | 2026-03-23 | 2026-03-27
VCFS-011 | Virtual Room | Implement CardLayout swap for Schedule View -> Virtual Room View | Taha | To Do | 0% | 2026-03-27 | 2026-04-01
VCFS-012 | Virtual Room | Develop post-session AttendanceOutcome logic (ATTENDED, NO_SHOW, ENDED_EARLY) | Taha | To Do | 0% | 2026-04-01 | 2026-04-05
VCFS-013 | Candidate UI | Develop Registration Screen & simulate session via Email String injection | MJAMishkat | Completed | 100% | 2026-03-16 | 2026-03-18
VCFS-014 | Booking Flow | Implement Manual Booking flow via Model queries | MJAMishkat | Completed | 100% | 2026-03-19 | 2026-03-24
VCFS-015 | Booking Flow | Build Auto-Booking Proposal/Acceptance UI View | MJAMishkat | To Do | 0% | 2026-03-24 | 2026-03-29
VCFS-016 | Virtual Room | Develop Lobby Gatekeeper: Cross-reference SystemTimer with Reservation StartTime | MJAMishkat | To Do | 0% | 2026-03-29 | 2026-04-04
VCFS-017 | Architecture | Visual Paradigm: Execute Round-Trip map of MVC Controller Dependencies | Mohamed | Completed | 100% | 2026-03-16 | 2026-03-19
VCFS-018 | QA Testing | JUnit 5: Boundary value equivalence testing for VirtualRoom entry/exit | Mohamed | In Progress | 15% | 2026-03-19 | 2026-03-25
VCFS-019 | QA Testing | JUnit 5: State verification tests for MeetingSession lifecycle | Mohamed | To Do | 0% | 2026-03-26 | 2026-03-31
VCFS-020 | Media | Draft precise 30-min chronological Panopto screencast script covering 12 Use Cases | Mohamed | To Do | 0% | 2026-04-01 | 2026-04-06

## VCFS Dashboard
VIRTUAL CAREER FAIR SYSTEM (VCFS)
Project Manager: | Zaid
Architecture: | Model-View-Controller (MVC) Java Swing
Total Technical Tickets: | 20